## Roles Breakdown
PROJECT TITLE | HOME AUTOMATION USING ARTIFICIAL INTELLIGENCE
PROJECT MANAGER | MAHESHWARMAN S/O BALAKRISHNAN (B031910007)
GROUP MEMBER(S) | MOHAMED TARIQ ALI BIN SALAMUDEEN ALI (B031910049)
COMPANY NAME | OurAI Sdn. Bhd.
DATE | 2021-12-04
GITHUB
ROLE(S)
MAHESHWARMAN | PROJECT MANAGER, PROCUREMENT MANAGER, PROJECT SCHEDULER, RISK MANAGER
MOHAMED TARIQ ALI | FINANCIAL ANALYST, QUALITY MANAGER, TECHNICAL MANAGER

## Consolidated RAM
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Procurement Manager | Risk Manager | Financial Analyst | Project Scheduler | Quality Manager | Technical Manager
Project Initiation
Project Charter | P | S | I | I | I | I | I
Project Charter Revision | A | P | I | I | S | I | I
Research | I | S | S | S | S | S | P
Stakeholders | P | P | S | S | S | S | I
Guidelines | A | P | S | S | S | S | I
Project Planning
Scope & Goal Setting | P | S | I | I | I | I | I
WBS | A | S | I | I | P | I | S
Resource Supplier Recuitment Plan | A | P | S | S | I | S | S
Delivery Service Recruitment Plan | A | P | S | S | I | S | I
Cost Management Plan | A | S | S | P | I | S | S
Risk Management Plan | A | I | P | S | S | S | S
Communication Plan | A | I | I | I | P | I | I
ERD | I | I | I | I | I | I | P
Data Collection | I | I | I | I | I | I | P
Project Execution
Resource Acquirement | I | P | I | S | S | A | I
Server Setup | I | I | I | I | S | I | P
Model Training & Testing Phase | I | I | I | I | S | A | P
Result Validation | A | I | S | I | I | P | S
Database Management | I | I | I | I | I | A | P
Prototype Testing & Validation | A | I | S | I | I | A | P
Issue Logs | I | I | S | I | S | P | P
Change Requests | P | S | S | S | S | A | P
Final Product Testing & Validation | A | I | S | I | I | A | P
Project Monitoring & Controlling
Change Request Approval | A | S | S | S | I | A | S
Project Progress Updates | A | I | I | I | I | A | P
Monitor Stakeholder Engagement | S | P | I | I | I | A | I
Cost Monitor & Control | S | P | I | I | I | A | I
Resource Monitor & Control | S | P | I | I | I | A | I
Project Closing
Final Product Release | P | S | I | I | P | A | P
Overall Project Review | I | I | I | I | I | A | I
Archive Documentation | I | I | I | I | I | I | I
Resources
P
A
S
I

## Project Initiation
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Procurement Manager | Risk Manager | Financial Analyst | Project Scheduler | Quality Manager | Technical Manager
Project Initiation
Project Charter | P | S | I | I | I | I | I
Project Charter Revision | A | P | I | I | S | I | I
Research | I | S | S | S | S | S | P
Stakeholders | P | P | S | S | S | S | I
Guidelines | A | P | S | S | S | S | I
Resources
P
A
S
I

## Project Planning
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Procurement Manager | Risk Manager | Financial Analyst | Project Scheduler | Quality Manager | Technical Manager
Project Planning
Scope & Goal Setting | P | S | I | I | I | I | I
WBS | A | S | I | I | P | I | S
Resource Supplier Recuitment Plan | A | P | S | S | I | S | S
Delivery Service Recruitment Plan | A | P | S | S | I | S | I
Cost Management Plan | A | S | S | P | I | S | S
Risk Management Plan | A | I | P | S | S | S | S
Communication Plan | A | I | I | I | P | I | I
ERD | I | I | I | I | I | I | P
Data Collection | I | I | I | I | I | I | P
Resources
P
A
S
I

## Project Execution
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Procurement Manager | Risk Manager | Financial Analyst | Project Scheduler | Quality Manager | Technical Manager
Project Execution
Resource Acquirement | I | P | I | S | S | A | I
Server Setup | I | I | I | I | S | I | P
Model Training & Testing Phase | I | I | I | I | S | A | P
Result Validation | A | I | S | I | I | P | S
Database Management | I | I | I | I | I | A | P
Prototype Testing & Validation | A | I | S | I | I | A | P
Issue Logs | I | I | S | I | S | P | P
Change Requests | P | S | S | S | S | A | P
Final Product Testing & Validation | A | I | S | I | I | A | P
Resources
P
A
S
I

## Project Monitoring&Controlling
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Procurement Manager | Risk Manager | Financial Analyst | Project Scheduler | Quality Manager | Technical Manager
Project Monitoring & Controlling
Change Request Approval | A | S | S | S | I | A | S
Project Progress Updates | A | I | I | I | I | A | P
Monitor Stakeholder Engagement | S | P | I | I | I | A | I
Cost Monitor & Control | S | P | I | I | I | A | I
Resource Monitor & Control | S | P | I | I | I | A | I
Resources
P
A
S
I

## Project Closing
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Procurement Manager | Risk Manager | Financial Analyst | Project Scheduler | Quality Manager | Technical Manager
Project Closing
Final Product Release | P | S | I | I | P | A | P
Overall Project Review | I | I | I | I | I | A | I
Archive Documentation | I | I | I | I | I | I | I
Resources
P
A
S
I