## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT MEMBERS | 1. MAHESHWARMAN S/O BALAKRISHNAN 2. MOHAMED TARIQ ALI BIN SALAMUDEEN ALI 3. MOHAMMED SADEQ NOMAN
PROJECT TITLE | HOME AUTOMATION USING ARTIFICIAL INTELLIGENCE
PROJECT MANAGER | MAHESHWARMAN S/O BALAKRISHNAN
COMPANY NAME | OurAI SDN. BHD.
DATE | 2021-10-11 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Mahesh | 2021-10-11 | 2021-10-14 | 3 | 100%
1.1.1 | Project Charter Revisions | Tariq | 2021-10-14 | 2021-10-15 | 1 | 100%
1.2 | Research | Sadeq | 2021-10-14 | 2021-10-20 | 6 | 65%
1.3 | Projections | Sadeq | 2021-10-15 | 2021-10-21 | 6 | 65%
1.4 | Stakeholders | Mahesh and Tariq | 2021-10-16 | 2021-10-21 | 5 | 25%
1.5 | Guidelines | Tariq | 2021-10-17 | 2021-10-22 | 5 | 0%
1.6 | Project Initiation | Tariq | 2021-10-22 | 2021-10-27 | 1 | 0%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Mahesh | 2021-10-27 | 2021-10-28 | 4 | 0%
2.2 | Budget | Tariq | 2021-10-29 | 2021-11-01 | 2 | 0%
2.3 | Communication Plan | Mahesh | 2021-11-01 | 2021-11-05 | 4 | 0%
2.4 | Risk Management | Sadeq | 2021-11-01 | 2021-11-05 | 4 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort & Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%